## Risk Matrix
Risk Matrix
SEVERITY → LIKELIHOOD ↓ | 1 - Minor | 2 - Serious | 3 - Fatal
3 - Probable | Medium -3- Awards given too often. Quality of nomination drops | High -6- Systemic bias in nominations. Widespread ethical misuse (reciprocal nominations). | High -9- Erosion of programme integrity and employee trust
2 - Possible | Low -2- Occasional incorrect contractor nominations caught early in approval flow. | Medium -4- Approval bottlenecks. Inconsistent scoring rubric application across locations. | High -6- Legal trouble from paying contractors. Data privacy issues on Viva Engage.
1 - Unlikely | Low -1- Single missed nomination. Minor delay in quarterly review cycle. | Low -2- Budget miscalculation due to late batch submissions. Exchange rate errors. | Medium -3- Reputational risk from a public misuse case; rejected nomination causing staff grievance.
Legend: | Low (1–2) | Medium (3–4) | High (6–9)

## Risk Register
Risk ID | Category | Risk Description | Likelihood (1–3) | Severity (1–3) | Score (L×S) | Risk Level | Impact if Risk Occurs | Mitigation / Controls | Owner
R01 | Ethical Use | Reciprocal or self-nominations submitted by employees | 3 | 3 | 9 | High | High Erosion of programme integrity and employee trust | One Star per quarter enforced by platform. Approval review by Recognition Team | Recognition Team
R02 | Bias/Fairness | Systemic visibility bias. Only high-profile roles nominated | 3 | 2 | 6 | High | High Demotivation of under-recognised employees. Cultural damage | Manager responsibility to surface less visible contributors. Panel bias checks | Line Managers
R03 | Legal/Compliance | Contractor receives or submits a nomination in breach of guidelines | 2 | 3 | 6 | High | High Legal liability and reputational harm to Version 1 | Platform eligibility gate. Contractor status checked at submission | Recognition Team
R04 | Data Privacy | Approved nominations posted publicly on Viva Engage without consent | 2 | 3 | 6 | High | High GDPR breach. Reputational and legal consequences | Communication plan to confirm recipient consent before public posting | HR / Comms
R05 | Process | Approval bottlenecks delay quarterly award cycle | 2 | 2 | 4 | Medium | Medium Delayed recognition. Reduced employee engagement | SLA on approval turnaround. escalation path defined in process | Recognition Team
R06 | Process | Inconsistent rubric scoring across regions / panels | 2 | 2 | 4 | Medium | Medium Unfair outcomes. Loss of confidence in scoring | Scoring rubric standardised. Panel session held each quarter for calibration purposes | Recognition Team
R07 | Reputational | Rejected nomination causes employee grievance or PR incident | 1 | 3 | 3 | Medium | Medium Employee relations issue. Negative publicity risk | Constructive written feedback on all rejections Re-submission permitted within quarter | HR
R08 | Budget/Integrity | Last-minute batch submissions complicate budget and review | 3 | 1 | 3 | Medium | Medium Budget overrun. Review process disruption | Submission deadline enforced. Late nominations deferred to next quarter | Finance / Recog Team
R09 | Process | New joiners excluded from recognition culture | 2 | 1 | 2 | Low | Low New joiners feel undervalued. Early disengagement | Manager onboarding checklist includes recognition programme introduction | Line Managers
R10 | Budget | Exchange rate errors in multi-region award values | 1 | 2 | 2 | Low | Low Incorrect award amounts paid out | Award values fixed in local currency per published table. This is reviewed annually | Finance
R11 | Process | Single missed nomination due to admin error | 1 | 1 | 1 | Low | Low Minor process gap; negligible programme impact | Quarterly review to confirm all eligible employees have had equal opportunity to nominate and be nominated | Recognition Team